## Sprint-1
Week #1 (7 hrs / week)
Backlog Items | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
28
Design Skeletal structure for Airport Management System | Actively took part in requirement gathering | Virag | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2
| Design basic database schema | Milan | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2
| Deciding Techstack to be used | Amika | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2
| Setup git environment for project | Dhruva | 6 | 0 | 0 | 0 | 3 | 1 | 1 | 1
| Designing the basic project structure | All | 4 |  |  |  | 1 | 1 | 1 | 1
|  | Total | 28 | 28 | 28 | 28 | 28 | 24 | 16 | 8
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Dhruva | 7 hours / Week
Amika | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-2
Week #2 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Continued with code changes implementation | Design login/signup page | Amika | 7 | 0 | 0 | 0 | 0 | 1 | 3 | 3
| Finalized the archietecture | Dhruva | 7 | 0 | 0 | 0 | 1 | 1 | 2 | 3
| Design Add/update page | Milan | 7 | 2 | 1 | 1 | 2 | 1 | 0 | 0
| Learn frontend technologies | Virag | 7 | 1 | 2 | 2 | 1 | 1 | 0 | 0
|  | Total | 28 | 25 | 22 | 19 | 15 | 11 | 6 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-3
Week #3 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Dashboard Deisgning, CRUD operation, Login/Signup | Create APIs with React | Amika | 7 | 0 | 2 | 0 | 0 | 3 | 0 | 2
| Completed UI for Login/Signup page | Dhruva | 7 | 0 | 0 | 3 | 2 | 0 | 0 | 2
| Add table for view page | Milan | 7 | 0 | 2 | 0 | 2 | 0 | 3 | 0
| Resolve APIs and fix bugs | Virag | 7 | 2 | 1 | 0 | 0 | 2 | 0 | 2
|  | Total | 28 | 26 | 21 | 18 | 14 | 9 | 6 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-4
Week #4 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Gate service, Terminal service, flight service | Tested Add flight page | Amika | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 4
| Start integration of frontend and backend page | Dhruva | 7 | 0 | 0 | 2 | 3 | 0 | 1 | 1
| Design view flight page | Milan | 7 | 0 | 0 | 0 | 0 | 0 | 4 | 3
| baggage routes and carousal routes | Virag | 7 | 0 | 0 | 0 | 0 | 3 | 4 | 0
|  | Total | 28 | 28 | 28 | 26 | 23 | 20 | 8 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-5
Week #5 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Permissions on different view pages, gate, terminal and baggage manipulation | Worked on database | Amika | 7 | 0 | 2 | 0 | 2 | 0 | 3 | 0
| Worked on backend services | Dhruva | 7 | 0 | 0 | 0 | 0 | 2 | 2 | 3
| Started integration of frontend and backend | Milan | 7 | 0 | 0 | 2 | 0 | 3 | 2 | 0
| Backend - baggage routes and carousal routes | Virag | 7 | 0 | 0 | 0 | 3 | 2 | 0 | 2
|  | Total | 28 | 28 | 26 | 24 | 19 | 12 | 5 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-6
Week #6 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Bug fixes, completion gate service, terminal service | Worked on designing assign baggage page | Amika | 7 | 0 | 0 | 2 | 2 | 3 | 0 | 0
| Test gate maintainance page | Dhruva | 7 | 0 | 0 | 0 | 2 | 2 | 2 | 1
| Started deploying on EC2 instance | Milan | 7 | 0 | 0 | 0 | 2 | 2 | 2 | 1
| Merge all the APIs for Add/update view flight page | Virag | 7 | 3 | 2 | 1 | 1 | 0 | 0 | 0
|  | Total | 28 | 25 | 23 | 20 | 13 | 6 | 2 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-7
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Gate assignment and gate freeing functionality | Tested all pages | Amika | 7 | 0 | 0 | 3 | 2 | 0 | 0 | 2
| Started deploying application with load balancer | Dhruva | 7 | 0 | 3 | 0 | 0 | 2 | 2 | 0
| Improved UI | Milan | 7 | 3 | 0 | 1 | 1 | 0 | 0 | 2
| Started documentation and end to end testing | Virag | 7 | 1 | 2 | 0 | 3 | 1 | 0 | 0
|  | Total | 28 | 24 | 19 | 15 | 9 | 6 | 4 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Amika | 7 hours / Week
Dhruva | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sprint-8
Week #7 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
28
Bug fixes and testing | Gate freeing logic | Amika | 7 | 0 | 0 | 0 | 3 | 2 | 0 | 2
| Update Page in frontend | Dhruva | 7 | 0 | 0 | 2 | 0 | 3 | 1 | 1
| Deploy application On AWS EC2 | Milan | 7 | 2 | 2 | 1 | 1 | 0 | 0 | 1
| Completed testing of application | Virag | 7 | 2 | 0 | 0 | 2 | 1 | 1 | 1
|  | Total | 28 | 24 | 22 | 19 | 12 | 7 | 5 | 0
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Team:
Dhruva | 7 hours / Week
Amika | 7 hours / Week
Milan | 7 hours / Week
Virag | 7 hours / Week
Total Available Hours During Sprint: | 28

## Burndown chart
Time |  | Tasks |  | Time |  | Tasks |  | Time |  | Tasks |  | Time |  | Tasks |  | Time |  | Tasks
Day | Dates | Planned | Actual | Day | Dates | Planned | Actual | Day | Dates | Planned | Actual | Day | Dates | Planned | Actual | Day | Dates | Planned | Actual | Time |  | Tasks |  | Time |  | Tasks |  | Time |  | Tasks
sun | 2022-10-02 | 10 | 10 | sun | 2022-10-09 | 10 | 10 | sun | 2022-10-16 | 10 | 10 | sun | 2022-10-23 | 9 | 9 | sun | 2022-10-30 | 10 | 10 | Day | Dates | Planned | Actual | Day | Dates | Planned | Actual | Day | Dates | Planned | Actual
mon | 2022-10-03 | 9 | 9 | mon | 2022-10-10 | 9 | 9 | mon | 2022-10-17 | 9 | 8 | mon | 2022-10-24 | 8 | 7 | mon | 2022-11-01 | 9 | 9 | sun | 2022-11-07 | 10 | 10 | sun | 2022-11-15 | 10 | 10 | sun | 2022-11-22 | 10 | 10
tue | 2022-10-04 | 8 | 7 | tue | 2022-10-11 | 7 | 7 | tue | 2022-10-18 | 7 | 7 | tue | 2022-10-25 | 8 | 7 | tue | 2022-11-02 | 8 | 7 | mon | 2022-11-08 | 9 | 9 | mon | 2022-11-16 | 9 | 9 | mon | 2022-11-23 | 9 | 9
wed | 2022-10-05 | 7 | 7 | wed | 2022-10-12 | 7 | 6 | wed | 2022-10-19 | 7 | 7 | wed | 2022-10-26 | 7 | 6 | wed | 2022-11-03 | 7 | 7 | tue | 2022-11-09 | 8 | 7 | tue | 2022-11-17 | 8 | 7 | tue | 2022-11-24 | 8 | 7
thurs | 2022-10-06 | 6 | 6 | thurs | 2022-10-13 | 6 | 6 | thurs | 2022-10-20 | 6 | 6 | thurs | 2022-10-27 | 6 | 6 | thurs | 2022-11-04 | 7 | 6 | wed | 2022-11-10 | 7 | 7 | wed | 2022-11-18 | 7 | 7 | wed | 2022-11-25 | 8 | 7
fri | 2022-10-07 | 6 | 6 | fri | 2022-10-14 | 6 | 6 | fri | 2022-10-21 | 5 | 4 | fri | 2022-10-28 | 5 | 5 | fri | 2022-11-05 | 6 | 6 | thurs | 2022-11-11 | 6 | 6 | thurs | 2022-11-19 | 6 | 6 | thurs | 2022-11-26 | 6 | 6
sat | 2022-10-08 | 6 | 5 | sat | 2022-10-15 | 5 | 4 | sat | 2022-10-22 | 4 | 4 | sat | 2022-10-29 | 5 | 5 | sat | 2022-11-06 | 5 | 5 | fri | 2022-11-13 | 6 | 6 | fri | 2022-11-20 | 6 | 6 | fri | 2022-11-27 | 6 | 6
[20 empty] | sat | 2022-11-14 | 5 | 5 | sat | 2022-11-21 | 6 | 5 | sat | 2022-11-28 | 5 | 5